## Master
| Process | Sub Process | Required | Person | Status | Comments | Worksheet
1) | Vobill Config | Current Voucher templates | VT's to be copied from PPFE to VOMS, no new templates required. | Renier | Done
|  |  | On implementation VOMS to produce 12 Digit Pins, once all Dealers are ready for 14 digit, templates to be update on VOMS. | Renier | Done
|  |  | Will we be required to update VT's on Vobill - PIN Length Field | Marius | To be done | Marius to update Voucher Templates on change over
|  |  | On implementation of VOMS on 15 May (after 5 Day close period) Vobill to run a production Pin Gen request for all active VT's to confirm 12 digit pin received from VOMS. | Marius | To be done | To be controlled, only test one VT at a time, only move to next once all is good.
|  |  | On the change over to 14 digit run test batch for each product, confirm pin length and other details - if incorrect Vobill will reject how will VOMS fix the file and resend to Vobill. | Kobus | To be done | Kobus confirmed manual roll back if no other option - handled on a case to case basis.
2) | Pin Generation | Test 12 Digit Pin Gen - all current active VT's | Confirm Pin Length, Batch Qty, Denom, Expiry Period | Dennis/Marius | In Progress | Issue with Pin length - Kobus working with developers to fix. Should be good for testing to start on 16 April. | a
|  | Test 14 Digit Pin Gen - all current active VT's | Confirm Pin Length, Batch Qty, Denom, Expiry Period | Dennis/Marius | To be done |  | a
|  | R0 Variable Voucher | Test Pin Gen for 12 & 14 digit | Dennis | To be done |  | a
3) | Pin Sync | Load Pin File | Both 12 & 14 digit pin files loaded successfully | Dennis | Cant be done on test, | Dennis confirm that sequence is correct in staging it should be good to sync - nothing in Vobill process
|  |  | Batch/Box sequence received from VOMS - will it follow on from PPFE | Renier | Done | VOMS to continue with sequence
|  | Storage | Test storage of both 12 and 14 – block 14 | Dennis | Done
|  |  | Reporting - split. Display both 12 & 14 digit stock | Dennis | Done
4) | Order Process | Customer Sales Order - CSO | Test CSO process for both 12 & 14 digit for EV | Marius/Edwena | Done
|  |  | Validate FIFO pin allocation from stock | Marius/Edwena | Done
|  | EV Print orders | Test process for both 12 & 14 digit | Marius/Edwena | Done
|  |  | Generate 14 digit pin ev print file for Factory | Dennis | To be done | Test file mailed to Kurt on 09 April 2020
|  |  | Physical voucher artwork no mention of 12 digit | Marius | Done | Kurt confirmed, all base stock checked.
|  |  | Physical voucher artwork - enough space to print 14 digit pin | Marius | Done
5) | Pin Transfer to VRMS |  | Pin Transfer to VRMS - 12 & 14 - BSO/CSO orders | Marius/Edwena | Done
|  |  | 12 & 14 digit pin packages created - Scrambling Dealer Orders | Dennis | Done
|  |  | Allocation request to VOMS | Dennis/Kobus | ? | Dennis to setup Vobill QA end test to VOMS QA
|  |  | Activation Request to VOMS | Dennis/Kobus | ? | Dennis to setup Vobill QA end test to VOMS QA
|  |  | Expired stock Termination | Dennis/Kobus | ? | Dennis to setup Vobill QA end test to VOMS QA
6) | Dealer Orders | Vodacom SP | Dealer order pin package created 12 & 14 digit | Dennis | Done
|  |  | Pin Encryption | Dennis | NA | PGP Encryption - Dennis, nothing changed in process, no need to test
|  |  | Pin Scrambling | Dennis | Done
|  | Smartcall | Pin Encryption | Dennis | NA | PGP Encryption - Dennis, nothing changed in process, no need to test
|  |  | Physical Voucher - Alloc/Activate/Termination test | Dennis
7) | Pin Stock Holding | Increase Pins stock | Additional pins required for change over - +/- 250m additional across all products | Edwena | In Progress
8) | Notifications | Vobill Notification | Approve Oder/Delivery Notifications. Report updates | Dennis | NA | PGP Encryption - Dennis, nothing changed in process, no need to test

## VT Templates
Vobill Info | [8 empty] | Validation
TEMPLATE | TEMPL_CODE | PRODUCT | Long Description | Expiry Period VT | DENOM | SALES_PRODUCT | VT_CODE | Comment1 | Expiry Months | Batch Size | Number of Batches | Pin Length | Allocation Req | Activation | Termination | All Ok | Note
2 | R55/TW90 | R55PIN |  |  | 55 | R55EV | 26 | To Test | [8 empty] | All items marked in Yellow to be tested.
2 | R55/TW90 | R55PIN |  |  | 55 | R55V | 25 | To Test | [8 empty] | Test Physical Voucher Alloc/act/termination for R55V
7 | R110/TW90 | R110PIN |  |  | 110 | R110V | 31
7 | R110/TW90 | R110PIN |  |  | 110 | R110EV | 32 | To Test
8 | R275/TW180 | R275PIN |  |  | 275 | R275EV | 36 | To Test
8 | R275/TW180 | R275PIN |  |  | 275 | R275V | 35
9 | R29/TW90 | R29PIN |  |  | 29 | R29EV PROMO | 49 | No SPs linked and deactivated
9 | R29/TW90 | R29PIN |  |  | 29 | R29V | 15
9 | R29/TW90 | R29PIN |  |  | 29 | R29EV | 16 | To Test
10 | R1/TW365 | R120PIN |  |  | 120 | R120EV | 52 | No SPs linked and deactivated
15 | R1100/TW365 | R1100PIN |  |  | 1100 | R1100EV | 38 | To Test
15 | R1100/TW365 | R1100PIN |  |  | 1100 | R1100V | 37
16 | R59/TW90 | R59PIN |  |  | 59 | R59V | 27 | No SPs linked and deactivated
16 | R59/TW90 | R59PIN |  |  | 59 | R59EV | 28 | No SPs linked and deactivated
18 | R13/TW1 | R12PIN |  |  | 11.99 | R13 EV | 54 | No SPs linked and deactivated
18 | R13/TW1 | R13 PIN |  |  | 13 | R13 EV | 54 | No SPs linked and deactivated
20 | R265/TW730 | R365 PIN |  |  | 265 | R365 V | 39 | No SPs linked and deactivated
20 | R265/TW730 | R365 PIN |  |  | 265 | R365 EV | 40 | No SPs linked and deactivated
22 | R60/TW90 | R60 YEBO5 PIN |  |  | 12 | R12EV PROMO | 48 | No SPs linked and deactivated
22 | R60/TW90 | R60 YEBO5 PIN |  |  | 12 | R12 EV | 42 | To Test
22 | R60/TW90 | R60 YEBO5 PIN |  |  | 12 | R60 YEBO5 V | 41 | To Test
25 | R49/TW30 | R49PIN |  |  | 49 | R49V | 43
25 | R49/TW30 | R49PIN |  |  | 49 | R49EV | 44 | To Test
26 | R20/TW90 | R20PIN B |  |  | 20 | R20V B | 501 | No SPs linked and deactivated
27 | R50/TW90 | TESTPROD |  |  | 50 | R50V B | 503 | No SPs linked and deactivated
28 | R100/TW90 | R100PIN B |  |  | 100 | R100V B | 505 | No SPs linked and deactivated
31 | R15/TW30 | R15PIN I |  |  | 15 | R15V I | 551 | No SPs linked and deactivated
34 | R100/TW60 | R100PIN K |  |  | 100 | R100V K | 535 | No SPs linked and deactivated
39 | R21/TW365 | R21PIN |  |  | 21 | R21 EV | 47 | No SPs linked and deactivated
53 | R25/TW90 | R25 YEBO5 PIN |  |  | 5 | R5 EV | 6 | To Test
53 | R25/TW90 | R25 YEBO5 PIN |  |  | 5 | R25 YEBO5 V | 5
54 | R1/TW30 | R1.00 PIN |  |  | 1 | R1.00EV | 998 | No SPs linked and deactivated
96 | R2/TW90 | R 2 PIN |  |  | 2 | R 2 EV | 96 | To Test
98 | R10/TW90 | R 10 PIN |  |  | 10 | R 10 EV | 98 | To Test
99 | R0 VAR/TW365 | R0 VARIABLE PIN |  |  | 0 | R0 VARIABLE PIN | 99 | To Test
4722 | P 60Min VB | P 60MIN VB PIN |  |  | 5 | P 60MIN VB | 4722 | To Test
4724 | P 10Min VB | P 10MIN VB PIN |  |  | 2 | P 10 MIN V B | 4724 | To Test
4724 | P 10Min VB | P 10MIN VB PIN |  |  | 2 | P 10 MIN VB V | 4720
4726 | P 50MB 1Hr DB | P 50MB 1HR PIN |  |  | 5 | P 50MB 1HR BD V | 4727
4726 | P 50MB 1Hr DB | P 50MB 1HR PIN |  |  | 5 | P 50 MB 1HR DB | 4726 | To Test
5003 | R9Data/TW30 | R9 DATA PIN |  |  | 9 | R9 DATA V | 5001 | No SPs linked and deactivated
5003 | R9Data/TW30 | R9 DATA PIN |  |  | 9 | R9 DATA EV | 5003 | No SPs linked and deactivated
5004 | R25Data/TW30 | R25 DATA PIN |  |  | 25 | R25 DATA V | 5002 | No SPs linked and deactivated
5004 | R25Data/TW30 | R25 DATA PIN |  |  | 25 | R25 DATA EV | 5004 | No SPs linked and deactivated
5199 | MYMEG15/104 | MYMEG15 PIN |  |  | 10 | MYMEG15 DB | 5199 | No SPs linked and deactivated
5202 | MYMEG30/105 | MYMEG30 PIN |  |  | 12 | MYMEG30 DB | 5202 | No SPs linked and deactivated
5203 | MYMEG100/106 | MYMEG100 PIN |  |  | 29 | MYMEG100 DB | 5203 | No SPs linked and deactivated
5204 | MYMEG250/107 | MYMEG250 PIN |  |  | 63 | MYMEG250 DB | 5204 | No SPs linked and deactivated
5205 | MYMEG500/108 | MYMEG500 PIN |  |  | 79 | MYMEG500 DB | 5205 | To Test
5206 | MYGIG1/109 | MYGIG1 PIN |  |  | 99 | MYGIG1 DB | 5206 | To Test
5215 | M50MBVT5215 | M 50MB PIN |  |  | 12 | M 50MB EV | 5215 | To Test
5216 | M150MBVT5216 | M 150MB PIN |  |  | 29 | M 150MB EV | 5216 | To Test
5217 | M325MBVT5217 | M 325MB PIN |  |  | 55 | M 325MB EV | 5217 | To Test
5208 | M3GBVT5208 | M 3GB PIN |  |  | 229 | M 3GB EV | 5208 | Products still under test - not released for PROD yet. Currently no teting required.
5209 | M5GBVT5209 | M 5GB PIN |  |  | 349 | M 5GB EV | 5209
5210 | M10GBVT5210 | M 10GB PIN |  |  | 469 | M 10GB EV | 5210
5211 | M20GBVT5211 | M 20GB PIN |  |  | 699 | M 20GB EV | 5211
5225 | D20MBVT5225 | D 20MB PIN |  |  | 5 | D 20MB EV | 5225
5226 | D60MBVT5226 | D 60MB PIN |  |  | 9 | D 60MB EV | 5226
5227 | D100MBVT5227 | D 100MB PIN |  |  | 15 | D 100MB EV | 5227
5228 | D250MBVT5228 | D 250MB PIN |  |  | 27 | D 250MB EV | 5228
5229 | W100MBVT5229 | W 100MB PIN |  |  | 17 | W 100MB EV | 5229
5230 | W250MBVT5230 | W 250MB PIN |  |  | 35 | W 250MB EV | 5230
5231 | W500MBVT5231 | W 500MB PIN |  |  | 60 | W 500MB EV | 5231
5232 | W1GBVT5232 | W 1GB PIN |  |  | 80 | W 1GB EV | 5232
5233 | W2GBVT5233 | W 2GB PIN |  |  | 120 | W 2GB EV | 5233
5234 | 14D1GBVT5234 | 14D 1GB PIN |  |  | 100 | 14D 1GB EV | 5234
5236 | 100MBR6VT5236 | 100MB R6M PIN |  |  | 119 | 100MB R6M EV | 5236
5237 | 250MBR6VT5237 | 250MB R6M PIN |  |  | 219 | 250MB R6M EV | 5237
5235 | M55MBVT5235 | M 55MB PIN |  |  | 25 | M 55MB EV | 5235 | No SPs linked and deactivated

## Dennis Master QA Test
Vobill Info | [8 empty] | Validation
TEMPLATE | TEMPLATE_CODE | PRODUCT_DESC | PROD_CODE | DENOM | SALES_PRODUCT | VT_CODE | Comment1 | Exp Mths | Batch Size | No.Batches | Pin Length | Order No | Allocation Req | Activation | Termination | All Ok | ComID | Note
2 | R55/TW90 | R 55 PIN vodago | R55PIN | 55 | R55EV | 26 | To Test | 40 | 100 | 10 | 12 | 11 | Y | Y | Y | Y | 86 | All items marked in Yellow to be tested.
2 | R55/TW90 | R 55 PIN vodago | R55PIN | 55 | R55V | 25 | To Test | 40 | 100 | 10 | 12 |  | Y | Y | Y | Y | 86 | Test Physical Voucher Alloc/act/termination for R55V
7 | R110/TW90 | R 110 PIN vodago | R110PIN | 110 | R110EV | 32 | To Test | 40 | 50 | 10 | 12 | 12 | Y |  |  | Y | 87 | PPFE M110.0 - Kobus to check Voucher Template Desc - Vobill R110/TW90
7 | R110/TW90 | R 110 PIN vodago | R110PIN | 110 | R110V | 31 |  | 40 | 50 | 10 | 12 |  | Y |  |  | Y | 87
8 | R275/TW180 | R 275 PIN vodago | R275PIN | 275 | R275EV | 36 | To Test | 40 | 20 | 10 | 12 | 13 | Y |  |  | Y | 85
8 | R275/TW180 | R 275 PIN vodago | R275PIN | 275 | R275V | 35 |  | 40 | 20 | 10 | 12 |  | Y |  |  | Y | 85
9 | R29/TW90 | R 29 PIN vodago | R29PIN | 29 | R29EV | 16 | To Test | 40 | 100 | 10 | 12 | 14 | Y |  |  | Y | 126
9 | R29/TW90 | R 29 PIN vodago | R29PIN | 29 | R29V | 15 |  | 40 | 100 | 10 | 12 |  | Y |  |  | Y | 126
15 | R1100/TW365 | R 1100 PIN vodago | R1100PIN | 1100 | R1100EV | 38 | To Test | 40 | 5 | 10 | 12 | 15 | Y |  |  | Y | 88
15 | R1100/TW365 | R 1100 PIN vodago | R1100PIN | 1100 | R1100V | 37 |  | 40 | 5 | 10 | 12 |  | Y |  |  | Y | 88
22 | R60/TW90 | R60 Yebo5 PIN | R60 YEBO5 PIN | 12 | R12 EV | 42 | To Test | 40 | 500 | 10 | 12 | 16 | Y |  |  | Y | 317 | PPFE R12/TW90 - Kobus to check Voucher Template Desc - Vobill R60/TW90
22 | R60/TW90 | R60 Yebo5 PIN | R60 YEBO5 PIN | 12 | R60 YEBO5 V | 41 | To Test | 40 | 500 | 10 | 12 |  | Y |  |  | Y | 317
25 | R49/TW30 | R49 SMS PIN | R49PIN | 49 | R49EV | 44 | To Test | 40 | 100 | 10 | 12 | 17 | Y |  |  | Y | 383
25 | R49/TW30 | R49 SMS PIN | R49PIN | 49 | R49V | 43 |  | 40 | 100 | 10 | 12 |  | Y |  |  | Y | 383
53 | R25/TW90 | R25 Yebo5 PIN | R25 YEBO5 PIN | 5 | R5 EV | 6 | To Test | 40 | 500 | 10 | 12 | 18 | Y |  |  | Y | 754
53 | R25/TW90 | R25 Yebo5 PIN | R25 YEBO5 PIN | 5 | R25 YEBO5 V | 5 |  | 40 | 500 | 10 | 12 |  | Y |  |  | Y | 754
96 | R2/TW90 | R2.00 Electronic PIN | R 2 PIN | 2 | R 2 EV | 96 | To Test | 40 | 500 | 10 | 12 | [5 empty] | 953
98 | R10/TW90 | R 10 Electronic PIN | R 10 PIN | 10 | R 10 EV | 98 | To Test | 40 | 500 | 10 | 12 | [5 empty] | 955
99 | R0 VAR/TW365 | R0 Variable Pin | R0 VARIABLE PIN | 0 | R0 VARIABLE PIN | 99 | To Test | 60 | 1000 | 10 | 12 | [5 empty] | 1285
4722 | P 60Min VB | P 60Min VB Pin | P 60MIN VB PIN | 5 | P 60MIN VB | 4722 | To Test | 40 | 100 | 10 | 12 | [5 empty] | 1287
4724 | P 10Min VB | P 10Min VB Pin | P 10MIN VB PIN | 2 | P 10 MIN V B | 4724 | To Test | 40 | 100 | 10 | 12 | [5 empty] | 1290
4724 | P 10Min VB | P 10Min VB Pin | P 10MIN VB PIN | 2 | P 10 MIN VB V | 4720 |  | 40 | 100 | 10 | 12 | [5 empty] | 1290
4726 | P 50MB 1Hr DB | P 50MB 1Hr Pin | P 50MB 1HR PIN | 5 | P 50 MB 1HR DB | 4726 |  | 40 | 100 | 10 | 12 | [5 empty] | 1291
4726 | P 50MB 1Hr DB | P 50MB 1Hr Pin | P 50MB 1HR PIN | 5 | P 50MB 1HR BD V | 4727 | To Test | 40 | 100 | 10 | 12 | [5 empty] | 1291
5205 | MYMEG500/108 | MyMeg500DB Pin - 30 Days | MYMEG500 PIN | 79 | MYMEG500 DB | 5205 | To Test | 40 | 20 | 10 | 12 | [5 empty] | 1318
5206 | MYGIG1/109 | MyGig1DB Pin - 30 Days | MYGIG1 PIN | 99 | MYGIG1 DB | 5206 | To Test | 40 | 20 | 10 | 12 | [5 empty] | 1320
5208 | M3GBVT5208 | Monthly 3GB PIN | M 3GB PIN | 229 | M 3GB EV | 5208 | To Test | 40 | 10 | 10 | 12 | [5 empty] | 1582
5209 | M5GBVT5209 | MONTHLY 5GB PIN | M 5GB PIN | 349 | M 5GB EV | 5209 | To Test | 40 | 5 | 10 | 12 | [5 empty] | 1585
5210 | M10GBVT5210 | MONTHLY 10GB PIN | M 10GB PIN | 469 | M 10GB EV | 5210 | To Test | 40 | 5 | 10 | 12 | [5 empty] | 1586
5211 | M20GBVT5211 | MONTHLY 20GB PIN | M 20GB PIN | 699 | M 20GB EV | 5211 | Products still under test - not released for PROD yet. Currently no testing required. | 40 | 5 | 10 | 12 | [5 empty] | 1587
5215 | M50MBVT5215 | Monthly 50MB PIN | M 50MB PIN | 12 | M 50MB EV | 5215 |  | 40 | 100 | 10 | 12 | [5 empty] | 1682
5216 | M150MBVT5216 | Monthly 150MB PIN | M 150MB PIN | 29 | M 150MB EV | 5216 |  | 40 | 50 | 10 | 12 | [5 empty] | 1683
5217 | M325MBVT5217 | Monthly 325MB PIN | M 325MB PIN | 55 | M 325MB EV | 5217 |  | 40 | 20 | 10 | 12 | [5 empty] | 1681
5225 | D20MBVT5225 | Daily 20MB PIN | D 20MB PIN | 5 | D 20MB EV | 5225 |  | 40 | 100 | 10 | 12 | [5 empty] | 1593
5226 | D60MBVT5226 | Daily 60MB PIN | D 60MB PIN | 9 | D 60MB EV | 5226 |  | 40 | 100 | 10 | 12 | [5 empty] | 1594
5227 | D100MBVT5227 | Daily 100MB PIN | D 100MB PIN | 15 | D 100MB EV | 5227 |  | 40 | 100 | 10 | 12 | [5 empty] | 1595
5228 | D250MBVT5228 | Daily 250MB PIN | D 250MB PIN | 27 | D 250MB EV | 5228 |  | 40 | 50 | 10 | 12 | [5 empty] | 1596
5229 | W100MBVT5229 | Weekly 100MB PIN | W 100MB PIN | 17 | W 100MB EV | 5229 |  | 40 | 100 | 10 | 12 | [5 empty] | 1597
5230 | W250MBVT5230 | Weekly 250MB PIN | W 250MB PIN | 35 | W 250MB EV | 5230 |  | 40 | 50 | 10 | 12 | [5 empty] | 1598
5231 | W500MBVT5231 | Weekly 500MB PIN | W 500MB PIN | 60 | W 500MB EV | 5231 |  | 40 | 20 | 10 | 12 | [5 empty] | 1605
5232 | W1GBVT5232 | Weekly 1GB PIN | W 1GB PIN | 80 | W 1GB EV | 5232 |  | 40 | 20 | 10 | 12 | [5 empty] | 1606
5233 | W2GBVT5233 | Weekly 2GB PIN | W 2GB PIN | 120 | W 2GB EV | 5233 |  | 40 | 20 | 10 | 12 | [5 empty] | 1607
5234 | 14D1GBVT5234 | 14Day 1GB PIN | 14D 1GB PIN | 100 | 14D 1GB EV | 5234 |  | 40 | 20 | 10 | 12 | [5 empty] | 1608
5236 | 100MBR6VT5236 | 100MB Recur 6 Months PIN | 100MB R6M PIN | 119 | 100MB R6M EV | 5236 |  | 40 | 10 | 10 | 12 | [5 empty] | 1610
5237 | 250MBR6VT5237 | 250MB Recur 6 Months PIN | 250MB R6M PIN | 219 | 250MB R6M EV | 5237 |  | 40 | 10 | 10 | 12 | [5 empty] | 1611